## Sheet1
Mdawi
Job Description |  | Development | OBJECTIVES By the end of each week the trainee should be able to:
Pattern Start Date |  | 2023-03-12
| Week 1 | General RAR Orientation / System Team Orientation/ PMO Orientation
| Week 2 | Planning & Business Requirements | 1- Analyze business requirements 2- Estimate resources required for this project
| Week 3 | Mockup Design | 1- Understand 8 Golden Rules of Interface Design 2- Translate business requirements into user interfaces
| Week 4 | UI/UX Testing | 1- Understand what is UI/UX Testing 2- Perform cognitive walkthrough testing and evaluate the system based on 8 Golden Rules
| Week 5 | Development Environment Setup | 1- Understand the basics of Git & GitHub 2- Setup remote repository 3- Find and use the suitable IDE for the project 4- Setup localhost server
| Week 6 | Database System Design | 1- Understand the concepts of database design 2- Evaluate a set of query using SQL
| Week 7 | Implementation | 1- Prioritize business requirements 2- Create responsive interfaces 3- Test the system to find bugs and fix them 4- Deliver the tasks within specified timeframe
| Week 8 | Implementation
| Week 9 | Implementation
| Week 10 | Implementation
| Week 11 | Feedbacks and Enhancements | 1- Adapt with changes in requirements
| Week 12 | Demo | 1- Demonstrate the software in action
| Week 13 | Documentation
| Week 14 | Final Report